## Pinnacle Mobility 2025 (Stores)
PINNACLE FUNNEL | HO FUNNEL MONTH | STATUS | Tcetra Communication-Remarks | Pinnacle Remarks | OPS Update | WELCOME EMAIL STATUS | WELCOME EMAIL RECEIVED DATE | TBV NO | TSP ID | VIDAPAY STATUS | STORE NAME | DEALER NAME | ADDRESS | CITY | STATE | ZIP | BGC ID | DOB | EIN | SSN | CONTACT NO | EMAIL ID | TBW NEW DEALER APP & TF & DEALER AGGREEMENT STATUS | PERMITS | DOCUMENTS SUBMITTED TO ONBOARDING | LEASE/LOI | LEASE/LOI DATE | SURVEY SUBMISSION DATE | SURVEY COMPLETION DATE | SURVEY STATUS | FLOOR PLAN RECEIVED STATUS | FLOOR PLAN RECEIVED DATE | FLOOR PLAN DISCUSSSED WITH DEALER | FLOOR PLAN APPROVED STATUS *DEALER | FLOOR PLAN APPROVED BY DEALER DATE | ORDER NUMBER | AMOUNT | TILES ORDER DATE | PRE-INSTALL SUBMISSION STATUS | PRE-INSTALL SUBMISSION DATE | FURNITURE DELIVERY DATE | FURNITURE INSTALL DATE | DEMO DEVICE SENT TO DEALER DATE | SPECTRIO | SPECTRIO SUBMISSION DATE | ALPHACOMM | ALPHACOM SUBMISSION DATE | B2B Installation Request Date | New Store Kit | PHONE ORDER | TSHIRTS | DECAL | LMS | PRINTER AVAILABLE | RETAIL READY DATE | RETAIL READY MONTH | PINNACLE AGREEMENTS | Modified By | Modification Date
|  | NEW STORE | [8 empty] | Muman Bros Wireless LLC | MR.IMRAN HASANALI MOMIN | 496 N Murray Blvd | Colorado Spring | CO | 80916 | BGC ID-356704573 | 1980-01-13 | 99-1355029 | 273-87-1178 |  | tbv.denver@gmail.com | 2024-11-25 | [6 empty] | PENDING | [27 empty] | gary@pinnaclemobility.com | 2025-03-26 19:20
MARCH-25 | MARCH-25 | NEW STORE | 3/31-Retail Ready |  |  | RECEIVED | 2025-02-20 | 1469 | 165336 | OK | DIGITAL UPNY INC | MR. KULWANT SINGH | 333 Ahmerst St | Buffalo | NY | 14207 | BGC ID-360428585 | 1990-02-02 | 99-4960986 | 817-75-0758 |  | digitalupny@gmail.com | 2024-10-29 |  | 2025-03-24 | LEASE | 2025-02-03 | 2024-11-14 | 2024-11-18 | COMPLETED | RECEIVED | 2024-12-03 | YES | APPROVED | 2025-03-08 | 190689 | 2476.72 | 2025-03-06 | SUBMITTED | 2025-03-21 | 2025-03-26 | 2025-03-31 | 2025-03-19 | SUBMITTED |  | NOT REQUIRED |  | 2025-03-18 |  | ORDERED |  |  | COMPLETED | YES | 2025-03-31 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-04-01 07:39
MAY-25 | MAY-25 | NEW STORE | 5/31-RETAIL READY | Install Date: 5/28/25 Fixture Delivery: 5/23/25 8 AM Estimated Retail Ready Date: 5/30/25 |  | RECEIVED | 2024-09-30 | 1119 | 163502 | OK | Muman Bros Wireless LLC | MR.IMRAN HASANALI MOMIN | 4801 Pecos st | Denver | CO | 80221 | BGC ID- 362970930 | 1980-01-13 | 99-1355029 | 273-87-1178 | 512-825-8821 | tbv.denver@gmail.com | 2024-09-03 | REQUIRED |  | LEASE | 2025-05-07 | 2024-11-13 | 2024-11-16 | COMPLETED | RECEIVED |  |  | APPROVED |  |  |  |  | SUBMITTED | 2025-05-19 | [7 empty] | 2025-05-21 | [5 empty] | YES | 2025-06-02 | MAY | RECEIVED | ops@pinnaclemobility.com | 2025-06-05 10:06
JANUARY-25 | JANUARY-25 | NEW STORE | 1/27-Retail Ready |  |  | RECEIVED | 2024-12-06 | 1283 | 164424 | OK | CORECOMP GROUP LLC | MR.MUBEEN MOHAMMAD | 3710 S Grand Blvd | St. Louis | MO | 63118 | BGC ID- 349386675 | 1966-07-31 | 84-4604907 | 327-82-1210 |  | mig4trade@yahoo.com | 2024-09-17 |  | 2024-12-12 | LEASE | 2024-12-04 | 2024-09-24 | 2024-10-05 | COMPLETED | RECEIVED | 2024-10-28 | YES | APPROVED | 2024-11-04 |  |  |  | SUBMITTED | 2025-01-03 | 2025-01-16 | 2025-01-17 | 2024-12-20 | SUBMITTED |  | NOT REQUIRED |  | 2025-01-02 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-01-27 | JANUARY | RECEIVED | gary@pinnaclemobility.com | 2025-03-26 19:20
|  | NEW STORE | Floor Plan Confirmation with Imran | [7 empty] | Muman Bros Wireless LLC | MR.IMRAN HASANALI MOMIN | 2700 W 10th St Suite 101 | Greeley | CO | 80631 | BGC ID-356704573 | 1980-01-13 | 99-1355029 | 273-87-1178 |  | tbv.denver@gmail.com | 2024-10-29 |  |  |  |  | 2024-11-02 | 2024-11-08 | COMPLETED | [27 empty] | gary@pinnaclemobility.com | 2025-03-26 19:20
JANUARY-25 | JANUARY-25 | NEW STORE | 1/31-Retail Ready |  |  | RECEIVED | 2024-11-12 | 1222 | 164170 | OK | DIGITAL UPNY INC | MR. KULWANT SINGH | 744 East Ridge Road | Rochester | NY | 14621 | BGC ID-360428585 | 1990-02-02 | 99-4960986 | 817-75-0758 |  | digitalupny@gmail.com | 2024-10-10 |  | 2024-12-10 | LEASE | 2024-11-02 | 2024-09-30 | 2024-10-08 | COMPLETED | RECEIVED | 2024-11-01 | YES | APPROVED | 2024-11-06 |  |  |  | SUBMITTED | 2025-01-24 | 2025-01-28 | 2025-01-31 | 2024-12-14 | SUBMITTED |  | NOT REQUIRED |  | 2024-12-18 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-01-31 | JANUARY | RECEIVED | gary@pinnaclemobility.com | 2025-03-28 19:40
FEBRUARY-25 | FEBRUARY-25 | NEW STORE | 2/27-Retail Ready |  |  | RECEIVED | 2024-11-19 | 1239 | 164239 | OK | TOTAL WIRELESS OF NEW ENGLAND INC | MRS.SYEDA ZUBDA NAQVI | 201 Exchange St | Chicopee | MA | 01031 | BGC ID-361417375 | 1957-02-10 | 33-1610327 | 005-69-4525 |  | totalwirelessne@gmail.com | 2024-11-05 |  | 2024-11-26 | LEASE | 2024-11-18 | 2024-10-16 | 2024-10-18 | COMPLETED | RECEIVED | 2024-11-11 | YES | APPROVED | 2024-11-18 |  |  |  | SUBMITTED | 2025-02-13 | 2025-02-20 | 2025-02-22 |  | SUBMITTED |  | NOT REQUIRED |  |  |  |  | ORDERED | ORDERED | COMPLETED | YES | 2025-02-27 | FEBRUARY | NOT REQUIRED | gary@pinnaclemobility.com | 2025-03-26 19:20
FEBRUARY-25 | FEBRUARY-25 | NEW STORE | 2/28-Retail Ready |  |  | RECEIVED | 2025-02-03 | 1414 | 164932 | OK | SUCCESS GROUP LLC | MRS.SHALINI KHURANA JAIN | 11034 E US Highway | Independence | MO | 64055 | BGC ID- 347825270 | 1979-08-02 | 93-4520322 | 755-76-8596 |  | tonib0924@gmail.com | 2025-01-07 |  | 2025-02-07 | LEASE | 2025-01-07 | 2024-11-26 | 2024-12-03 | COMPLETED | RECEIVED | 2025-01-27 | YES | APPROVED | 2025-01-30 |  |  | 2025-02-11 | SUBMITTED | 2025-02-21 | 2025-02-27 | 2025-02-28 |  | SUBMITTED |  | NOT REQUIRED |  | 2025-02-10 |  |  |  |  | COMPLETED | YES | 2025-02-28 | FEBRUARY | NOT REQUIRED | gary@pinnaclemobility.com | 2025-04-10 12:27
JANUARY-25 | JANUARY-25 | NEW STORE | 1/27-Retail Ready |  |  | RECEIVED | 2024-12-31 | 1350 | 164622 | OK | AMA Group NY LLC | MRS.SHALINI KHURANA JAIN | 114-14 sutphin Blvd | Jamaica | NY | 11434 | BGC ID- 347825270 | 1979-08-02 | 33-2099299 | 755-76-8596 |  | tonib0924@gmail.com | 2024-12-20 |  | 2025-01-08 | LEASE | 2024-12-20 | 2024-11-23 | 2024-12-17 | COMPLETED | RECEIVED | 2024-12-30 | YES | APPROVED | 2024-12-30 |  |  | 2024-12-31 | SUBMITTED | 2025-01-16 | 2025-01-20 | 2025-01-23 | 2025-01-21 | SUBMITTED |  | NOT REQUIRED |  | 2025-01-13 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-01-27 | JANUARY | RECEIVED | gary@pinnaclemobility.com | 2025-04-10 12:27
APRIL-25 | APRIL-25 | NEW STORE | 4/24- Retail Ready |  |  | RECEIVED | 2024-12-19 | 1336 | 164552 | OK | DIGITAL UPNY INC | MR. KULWANT SINGH | 43 Niagara St | Tonawanda | NY | 14150 | BGC ID-360428585 | 1990-02-02 | 99-4960986 | 817-75-0758 | 585-500-0002 | digitalupny@gmail.com | 2024-11-25 |  | 2024-12-26 | LEASE | 2024-11-27 | 2024-11-23 | 2024-12-02 | COMPLETED | RECEIVED | 2024-12-10 | YES | APPROVED | 2024-12-16 |  |  | EXCEPTION | SUBMITTED | 2025-04-12 | 2025-04-18 | 2025-04-21 | 2025-04-15 | SUBMITTED | 2025-04-09 | SUBMITTED | 2025-04-09 | 2025-04-10 | Tracking #: PITT OHIO - 5050152366 - ETA | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-24 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-04-25 07:13
JANUARY-25 | JANUARY-25 | NEW STORE | 1/31-Retail Ready |  |  | RECEIVED | 2025-01-22 | 1398 | 164794 | OK | PINNACLEMOBILITY NY INC | MR.CHRIS CHRISTOFOROU | 799 Grand St | Brooklyn | NY | 11211 | BGC ID-365226260 | 1960-08-28 | 93-1565810 | 092-56-9344 |  | info@pinnaclemobility.com | 2025-01-06 |  | 2025-01-27 | LEASE | 2025-01-06 | 2024-12-24 | 2025-01-06 | COMPLETED | RECEIVED | 2025-01-16 | YES | APPROVED | 2025-01-20 |  |  |  | SUBMITTED | 2025-01-24 | 2025-01-28 | 2025-01-29 |  | SUBMITTED |  | NOT REQUIRED |  | 2025-01-28 |  | ORDERED | PENDING | PENDING | PENDING | YES | 2025-01-31 | JANUARY | NOT REQUIRED | gary@pinnaclemobility.com | 2025-03-28 19:40
FEBRUARY-25 | FEBRUARY-25 | NEW STORE | 2/26-Retail Ready |  |  | RECEIVED | 2025-02-10 | 1431 | 164998 | OK | Horizon Handy Phone Systems Inc | MR.AYUB KHAN | 563 86th St | Brooklyn | NY | 11209 | BGC ID-346341817 | 1973-09-13 | 93-3849820 | 1078-64-867 |  | ayub244khan@gmail.com | 2025-01-29 |  |  | LEASE | 2025-02-04 | 2025-01-20 | 2025-01-27 | COMPLETED | RECEIVED | 2025-02-04 | YES | APPROVED | 2025-02-06 |  |  | 2025-02-06 | SUBMITTED | 2025-02-16 | 2025-02-19 | 2025-02-20 |  | SUBMITTED |  | NOT REQUIRED |  | 2025-02-17 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-02-26 | FEBRUARY | RECEIVED | gary@pinnaclemobility.com | 2025-03-26 19:20
MARCH-25 | MARCH-25 | NEW STORE | 3/31-Retail Ready |  |  | RECEIVED | 2024-12-19 | 1337 | 164556 | OK | Muman Bros Wireless LLC | MR.IMRAN HASANALI MOMIN | 542 S Academy | Colorado Spring | CO | 80910 | BGC ID- 362970930 | 1980-01-13 | 99-1355029 | 273-87-1178 |  | tbv.denver@gmail.com | 2024-09-28 |  | 2024-12-26 | LEASE | 2025-02-10 | 2024-10-25 | 2024-11-01 | COMPLETED | RECEIVED | 2024-12-11 | YES | APPROVED | 2024-12-18 |  |  | 2024-12-09 | SUBMITTED | 2025-03-23 | 2025-03-26 | 2025-03-27 | 2025-03-25 | SUBMITTED |  | NOT REQUIRED |  | 2025-01-16 | Tracking #: AAA COOPER - 662199066 - ETA 3/28 |  |  |  | COMPLETED |  | 2025-03-31 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-03-31 19:45
JANUARY-25 | JANUARY-25 | NEW STORE | 1/31-Retail Ready |  |  | RECEIVED | 2024-12-18 | 1327 | 164554 | OK | Muman Bros Wireless LLC | MR.IMRAN HASANALI MOMIN | 1955 W Uintah St | Colorado Spring | CO | 80904 | BGC ID- 362970930 | 1980-01-13 | 99-1355029 | 273-87-1178 |  | tbv.denver@gmail.com | 2024-09-28 |  | 2024-12-26 | LEASE | 2024-12-17 | 2024-10-25 | 2024-10-30 | COMPLETED | RECEIVED | 2024-11-25 | YES | APPROVED | 2024-12-03 |  |  | 2024-12-03 | SUBMITTED | 2025-01-27 | 2025-01-29 | 2025-01-30 |  | SUBMITTED |  | NOT REQUIRED |  | 2025-01-16 | [6 empty] | 2025-01-31 | JANUARY | RECEIVED | gary@pinnaclemobility.com | 2025-03-26 19:20
JANUARY-25 | JANUARY-25 | NEW STORE | 1/17-Retail Ready |  |  | RECEIVED | 2024-12-18 | 1303 | 164468 | OK | Muman Bros Wireless LLC | MR.IMRAN HASANALI MOMIN | 3058 W Northern Ave | Pubelo | CO | 81005 | BGC ID- 362970930 | 1980-01-13 | 99-1355029 | 273-87-1178 |  | tbv.denver@gmail.com | 2024-09-30 |  | 2024-12-17 | LEASE | 2024-12-10 | 2024-10-28 | 2024-10-30 | COMPLETED | RECEIVED | 2024-11-06 | YES | APPROVED | 2024-12-03 |  |  | 2024-12-03 | SUBMITTED | 2024-12-29 | 2025-01-03 | 2025-01-08 | 2024-12-23 | SUBMITTED |  | NOT REQUIRED |  | 2024-12-18 |  | ORDERED |  | ORDERED | COMPLETED | YES | 2025-01-17 | JANUARY | RECEIVED | gary@pinnaclemobility.com | 2025-03-26 19:20
JANUARY-25 | JANUARY-25 | NEW STORE | 1/16-Retail Ready |  |  | RECEIVED | 2024-12-18 | 1326 | 164553 | OK | 786 COPIAGUE INC | MR.KAMIL U REHMAN | 116 E Fordham Rd | Bronx | NY | 10468 | BGC ID- 324838372 | 1980-04-14 | 99-0445080 | 156-592-021 |  | 786verizon@gmail.com | 2024-12-12 |  | 2024-12-27 | LEASE | 2024-12-12 | 2024-11-23 | 2024-12-17 | COMPLETED | RECEIVED | 2024-12-13 | YES | APPROVED | 2024-12-16 |  |  | 2024-12-16 | SUBMITTED | 2024-12-26 | 2025-01-09 | 2025-01-10 | 2025-01-07 | SUBMITTED |  | NOT REQUIRED |  | 2025-01-07 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-01-16 | JANUARY | RECEIVED | gary@pinnaclemobility.com | 2025-03-26 19:20
MARCH-25 | MARCH-25 | NEW STORE | 3/28-Retail Ready |  |  | RECEIVED | 2024-12-03 | 1268 | 164374 | OK | CORECOMP GROUP LLC | MR.MUBEEN MOHAMMAD | 2456 W CLAY ST | St. Charles | MO | 63301 | BGC ID- 349386675 | 1966-07-31 | 84-4604907 | 327-82-1210 |  | mig4trade@yahoo.com | 2025-03-01 | [6 empty] | COMPLETED | RECEIVED | 2024-12-05 | YES | APPROVED |  |  |  |  | SUBMITTED | 2025-03-07 | 2025-03-17 | 2025-03-25 | 2025-03-18 | SUBMITTED |  | NOT REQUIRED |  | 2025-03-18 | Tracking #: DOUBLE D EXPRESS - DB39282736 - ETA 3/19 | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-03-28 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-06-05 09:35
JANUARY-25 | JANUARY-25 | NEW STORE |  |  |  | RECEIVED | 2025-01-08 | 1367 | 164679 | OK | SUCCESS GROUP LLC | MRS.SHALINI KHURANA JAIN | 12200 15th St, 118 | Grandview | MO | 64030 | BGC ID- 347825270 | 1979-08-02 | 93-4520322 | 755-76-8596 |  | tonib0924@gmail.com | 2024-09-27 |  | 2025-01-17 | LEASE | 2025-01-08 | 2024-11-07 | 2024-11-11 | COMPLETED | RECEIVED | 2024-11-14 | YES | APPROVED | 2024-12-03 |  |  | 2024-12-11 | SUBMITTED | 2025-01-20 | 2025-01-27 | 2025-01-27 | 2025-01-25 | SUBMITTED |  | NOT REQUIRED |  | 2025-01-29 |  | ORDERED | PENDING | ORDERED | COMPLETED | YES | 2025-01-30 | JANUARY | RECEIVED | ops@pinnaclemobility.com | 2025-06-05 10:45
JANUARY-25 | JANUARY-25 | NEW STORE | 1/31-Retail Ready |  |  | RECEIVED | 2025-01-22 | 1399 | 164797 | OK | 799 Grand Street Wireless LLC | MR.KUMAIL SYED ZAIDI | 252 knickerbocker Ave | Brooklyn | NY | 11237 | BGC ID- 365252455 | 1987-07-17 | 33-2583486 | 827-71-3613 |  | skhzaidi@hotmail.com | 2025-01-04 |  | 2025-01-28 | LEASE | 2025-01-21 | 2025-01-06 | 2025-01-10 | COMPLETED | RECEIVED | 2025-01-16 | YES | APPROVED | 2025-01-20 |  |  |  | SUBMITTED | 2025-01-28 | 2025-01-29 | 2025-01-29 | 2025-01-31 | SUBMITTED |  | NOT REQUIRED |  | 2025-01-28 |  | ORDERED | PENDING | PENDING | PENDING | YES | 2025-01-31 | JANUARY | RECEIVED | gary@pinnaclemobility.com | 2025-03-26 19:20
FEBRUARY-25 | FEBRUARY-25 | NEW STORE | 2/17-Retail Ready |  |  | RECEIVED | 2025-01-29 | 1410 | 164921 | OK | HND WIRELESS LLC | MR.HARIS AMJAD | 1600 Pitkin Ave | Brooklyn | NY | 11212 | BGC ID- 339632683 | 1995-10-02 | 92-2722435 | 677-40-9638 |  | harisamjad3809@gmail.com | 2025-01-08 |  | 2025-02-04 | LEASE | 2025-01-28 | 2025-01-10 | 2025-01-21 | COMPLETED | RECEIVED | 2025-01-27 | YES | APPROVED | 2025-01-28 |  |  | 2025-01-24 | SUBMITTED | 2025-02-07 | 2025-02-12 | 2025-02-13 | 2025-02-11 | SUBMITTED |  | NOT REQUIRED |  | 2025-02-04 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-02-17 | FEBRUARY | RECEIVED | gary@pinnaclemobility.com | 2025-03-26 19:20
FEBRUARY-25 | FEBRUARY-25 | NEW STORE | 2/28-Retail Ready |  | 4/10/25-alfacomm signed document recieved and mailed | RECEIVED | 2025-02-03 | 1417 | 164931 | OK | ELITE TRADING INC | MR.YAZAN I ALKALABANI | 326 15TH STREET | TUSCALOOSA | AL | 35401 | BGC ID- 365464290 | 2001-11-17 | 33-2216421 | 417-65-3937 | 205-240-1673 | abekalabani@yahoo.com | 2025-01-15 |  | 2025-02-18 | LEASE | 2025-01-15 | 2024-11-08 | 2024-11-19 | COMPLETED | RECEIVED | 2025-01-22 | YES | APPROVED | 2025-02-03 |  |  | 2025-02-05 | SUBMITTED | 2025-02-21 | 2025-02-24 | 2025-02-26 | 2025-02-24 | SUBMITTED |  | SUBMITTED | 2025-04-10 | 2025-02-18 | [5 empty] | YES | 2025-02-28 | FEBRUARY | RECEIVED | ops@pinnaclemobility.com | 2025-04-10 09:53
MARCH-25 | MARCH-25 | NEW STORE | 3/31-Retail Ready |  |  | RECEIVED | 2025-02-03 | 1413 | 164933 | OK | TOTAL WIRELESS OF NEW ENGLAND INC | MRS.SYEDA ZUBDA NAQVI | 935 Riverdale st | West Springfield | MA | 01809 | BGC ID-361417375 | 1957-02-10 | 33-1610327 | 005-69-4525 |  | totalwirelessne@gmail.com | 2024-11-19 |  | 2025-02-06 | LEASE | 2025-01-23 | 2025-01-15 | 2025-01-23 | COMPLETED | RECEIVED | 2025-01-29 | YES | APPROVED | 2025-01-30 |  |  |  | SUBMITTED | 2025-03-25 | 2025-03-27 | 2025-03-27 | 2025-03-26 | SUBMITTED |  | NOT REQUIRED |  | 2025-03-18 | Tracking #: ESTES- 0285805006 - ETA |  |  |  | COMPLETED |  | 2025-03-31 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-03-31 20:03
FEBRUARY-25 | MARCH-25 | OWNERSHIP CHANGE | 3/17-Retail Ready |  | 4/12-onwer ship change | RECEIVED | 2025-02-11 | 0447 | 165222 | OK | Infinitytel Inc | MR.KAVLEEN S KOHLI | 428 CLINTON ST | HEMPSTEAD | NY | 11550 | BGC ID-360656991 | 1979-12-13 | 33-1395369 |  |  | infinitytel34@gmail.com | 2025-02-10 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED |  |  | NOT REQUIRED |  |  | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | COMPLETED | YES | 2025-03-17 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-06-05 09:23
APRIL-25 | APRIL-25 | NEW STORE | 4/28- Retail Ready |  |  | RECEIVED | 2025-04-07 | 1561 | 165644 | OK | TOTAL WIRELESS OF NEW ENGLAND INC | MRS.SYEDA ZUBDA NAQVI | 2460 Main ST Suite 118 | Springfield | MA | 01107 | BGC ID-361417375 | 1957-02-10 | 33-1610327 | 005-69-4525 | 516-813-8628 | totalwirelessne@gmail.com | 2024-12-03 |  | 2025-04-03 | LEASE | 2025-04-08 | 2025-01-15 | 2025-01-22 | COMPLETED | RECEIVED | 2025-03-27 | YES | APPROVED | 2025-04-04 |  |  | EXCEPTION | SUBMITTED | 2025-04-08 | 2025-04-21 | 2025-04-22 | 2025-04-22 | SUBMITTED | 2025-04-10 | SUBMITTED | 2025-04-10 | 2025-04-10 | Tracking #: ESTES - 0285799596 - ETA 4/24 | ORDERED | ORDERED | ORDERED | COMPLETED | NO | 2025-04-28 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-04-28 13:56
FEBRUARY-25 | FEBRUARY-25 | NEW STORE | 2/28-Retail Ready |  |  | RECEIVED | 2025-02-13 | 1453 | 165200 | OK | TOTAL WIRELESS OF NEW ENGLAND INC | MRS.SYEDA ZUBDA NAQVI | 1948 Park St | Hartford | CT | 06106 | BGC ID-361417375 | 1957-02-10 | 33-1610327 | 005-69-4525 | 516-813-8628 | totalwirelessne@gmail.com | 2025-02-05 |  | 2025-02-20 | LEASE | 2025-02-13 | 2025-01-24 | 2025-01-30 | COMPLETED | RECEIVED | 2025-02-11 | YES | APPROVED | 2025-02-12 |  |  | 2025-02-12 | SUBMITTED | 2025-02-21 | 2025-02-26 | 2025-02-27 |  | SUBMITTED |  |  |  | 2025-02-25 |  |  |  |  | COMPLETED | YES | 2025-02-28 | FEBRUARY | RECEIVED | ops@pinnaclemobility.com | 2025-04-08 13:39
MARCH-25 | MARCH-25 | NEW STORE | 3/28-Retail Ready |  |  | RECEIVED | 2025-03-07 | 1504 | 165409 | OK | TOTAL WIRELESS OF NEW ENGLAND INC | MRS.SYEDA ZUBDA NAQVI | 580 Main St | Middletown | CT | 06457 | BGC ID-361417375 | 1957-02-10 | 33-1610327 | 005-69-4525 | 516-813-8628 | totalwirelessne@gmail.com | 2025-02-27 |  | 2025-03-10 | LEASE | 2025-02-27 | 2025-01-24 | 2025-01-30 | COMPLETED | RECEIVED | 2025-03-03 | YES | APPROVED | 2025-03-05 | 190690 | 5488.06 | 2025-03-06 | SUBMITTED | 2025-03-21 | 2025-03-25 | 2025-03-25 | 2025-03-26 | SUBMITTED |  | NOT REQUIRED |  | 2025-03-18 | Tracking #: ESTES - 0285805003 - ETA | PENDING | PENDING | PENDING | COMPLETED | YES | 2025-03-28 | MARCH | RECEIVED | ops@pinnaclemobility.com | 2025-04-08 13:39
FEBRUARY-25 | FEBRUARY-25 | NEW STORE | 2/28-Retail Ready |  |  | RECEIVED | 2025-02-13 | 1451 | 165201 | OK | MMRK Enterprises LLC | MR.KUMAIL SYED ZAIDI | 422 Uniondale Ave | Uniondale | NY | 11553 | BGC ID- 365252455 | 1987-07-17 | 82-5371582 | 827-71-3613 |  | skhzaidi@hotmail.com | 2025-01-31 |  |  | LEASE | 2025-01-31 | 2025-01-24 | 2025-01-28 | COMPLETED | RECEIVED | 2025-02-04 | YES | APPROVED | 2025-02-06 |  |  | 2025-02-12 | SUBMITTED | 2025-02-24 |  |  |  | SUBMITTED |  | NOT REQUIRED |  | 2025-02-24 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-02-28 | FEBRUARY | RECEIVED | gary@pinnaclemobility.com | 2025-03-26 19:20
APRIL-25 | APRIL-25 | NEW STORE | 4/25- Retail Ready |  |  | RECEIVED | 2025-04-07 | 1536 | 165645 | OK | MAK COMMUNICATIONS INC | MR.MOHAMMAD AZAM AKRA KHAN | 10142 Hammerly Blvd | Houston | TX | 77080 | BGC ID-366220759 | 1970-07-07 | 33-3152926 | 841-46-5229 | 713-730-9888 | khan@myyahoo.com | 2025-03-05 |  | 2025-04-07 | LEASE | 2025-03-05 | 2025-02-27 | 2025-03-07 | COMPLETED | RECEIVED | 2025-03-14 | NO | APPROVED | 2025-04-01 |  |  | EXCEPTION | SUBMITTED | 2025-04-17 | 2025-04-21 | 2025-04-21 | 2025-04-21 | SUBMITTED | 2025-04-07 | SUBMITTED | 2025-04-07 | 2025-04-10 | Tracking #: AAA COOPER - 618237721 - ETA 4/24 | PENDING | PENDING | PENDING | COMPLETED | YES | 2025-04-25 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-05-01 07:25
FEBRUARY-25 | FEBRUARY-25 | NEW STORE | 2/28-Retail Ready |  |  | RECEIVED | 2025-02-11 | 1438 | 165064 | OK | DIGITAL UPNY INC | MR. KULWANT SINGH | 836 N Goodman Rd | Rochester | NY | 14609 | BGC ID-360428585 | 1990-02-02 | 99-4960986 | 817-75-0758 |  | digitalupny@gmail.com | 2025-02-03 |  | 2025-02-18 | LEASE | 2025-02-05 | 2025-01-27 | 2025-01-30 | COMPLETED | RECEIVED | 2025-02-06 | YES | APPROVED | 2025-02-10 |  |  | 2025-02-14 | SUBMITTED | 2025-02-26 |  |  |  | SUBMITTED |  |  |  | 2025-02-26 | Tracking #: TFORCE - 485084456 - DEL 3/3 |  |  |  | COMPLETED | YES | 2025-02-28 | FEBRUARY | RECEIVED | gary@pinnaclemobility.com | 2025-03-28 19:40
FEBRUARY-25 | FEBRUARY-25 | NEW STORE | 2/28-Retail Ready |  |  | RECEIVED | 2025-02-20 | 1470 | 165300 | OK | ALON MARS NETWORK INC | MR.GHULAM MUSTAFA ALI | 1318 Flatbush Ave | Brooklyn | NY | 11210 | BGC ID-366221374 | 1998-02-19 | 33-3341659 | 140-04-8360 | 215-778-8655 | alonmarsnetwork@gmail.com | 2025-02-11 |  | 2025-02-25 | LEASE | 2025-02-14 | 2025-02-04 | 2025-02-07 | COMPLETED | RECEIVED | 2025-02-17 | YES | APPROVED | 2025-02-19 |  |  | 2025-02-11 | SUBMITTED | 2025-02-24 | 2025-02-27 | 2025-02-28 |  | SUBMITTED |  | NOT REQUIRED |  | 2025-02-25 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-02-28 | FEBRUARY | RECEIVED | gary@pinnaclemobility.com | 2025-04-04 11:08
FEBRUARY-25 | MARCH-25 | OWNERSHIP CHANGE | 3/5-Retail Ready |  |  | RECEIVED | 2025-02-11 | 0052 | 165081 | OK | WIRELESS WORLD GROUP LLC | MR.PAWAN BHATIA | 1830 COLLEGE POINT BLVD, | COLLEGE POINT | NY | 11356 | BGC ID- 353774017 | 1984-02-07 | 83-1283326 | 054-90-6884 |  | wirelessexperts113@gmail.com | 2025-02-07 |  | 2025-02-19 | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED |  | NOT REQUIRED |  |  |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-03-05 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-06-05 09:23
FEBRUARY-25 | MARCH-25 | OWNERSHIP CHANGE | 3/11-Retail Ready |  |  |  |  | 0108 | 165082 | OK | WIRELESS WORLD GROUP LLC | MR.PAWAN BHATIA | 113-04 LIBERTY AVE | SOUTH RICHMOND HILL | NY | 11419 | BGC ID- 353774017 | 1984-02-07 | 83-1283326 | 054-90-6884 |  | wirelessexperts113@gmail.com | 2025-02-07 |  | 2025-02-27 | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED |  | NOT REQUIRED |  |  |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-03-12 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-06-05 09:23
FEBRUARY-25 | MARCH-25 | OWNERSHIP CHANGE | 3/10-Retail Ready |  |  | RECEIVED | 2025-02-12 | 0102 | 165072 | OK | WIRELESS WORLD GROUP LLC | MR.PAWAN BHATIA | 9501 JAMAICA AVE | WOODHAVEN | NY | 11421 | BGC ID- 353774017 | 1984-02-07 | 83-1283326 | 054-90-6884 |  | wirelessexperts113@gmail.com | 2025-02-07 |  | 2025-02-27 | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED |  | NOT REQUIRED |  |  |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-03-10 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-06-05 09:23
FEBRUARY-25 | MARCH-25 | OWNERSHIP CHANGE | 3/10-Retail Ready |  |  |  |  | 0259 | 165085 | OK | WIRELESS WORLD GROUP LLC | MR.PAWAN BHATIA | 10817 101ST AVE | SOUTH RICHMOND HILL | NY | 11419 | BGC ID- 353774017 | 1984-02-07 | 83-1283326 | 054-90-6884 |  | wirelessexperts113@gmail.com | 2025-02-07 |  | 2025-02-19 | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED |  | NOT REQUIRED |  |  |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-03-10 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-06-05 09:23
FEBRUARY-25 | MARCH-25 | OWNERSHIP CHANGE | 3/6-Retail Ready |  |  | RECEIVED | 2025-02-11 | 0943 | 161525 | OK | WIRELESS WORLD GROUP LLC | MR.PAWAN BHATIA | 12801 LIBERTY AVE | SOUTH RICHMOND HILL,NY 11419 | NY | 11419 | BGC ID- 353774017 | 1984-02-07 | 83-1283326 | 054-90-6884 |  | wirelessexperts113@gmail.com | 2025-02-07 |  | 2025-02-19 | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED |  | NOT REQUIRED |  |  |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-03-06 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-06-05 09:23
MARCH-25 | MARCH-25 | NEW STORE | 3/31-Retail Ready |  |  | RECEIVED | 2025-03-13 | 1508 | 165434 | OK | ONS Services LLC | MRS.NAMITA SAHNI | 725 South 14th St | Kingsville | TX | 78363 | BGC ID- 357087713 | 1968-05-19 | 33-1427375 | 085-80-8221 |  | sahniny@snnmservices.com | 2025-02-12 |  | 2025-03-19 | LEASE | 2025-02-14 | 2025-02-21 | 2025-02-28 | COMPLETED | RECEIVED | 2025-03-06 | YES | APPROVED | 2025-03-07 | 190729 | 3679.07 | 2025-03-07 | SUBMITTED | 2025-03-27 | 2025-03-29 | 2025-03-31 | 2025-03-26 | SUBMITTED |  | NOT REQUIRED |  | 2025-03-18 | Tracking #: AAA COOPER - 574536975 - ETA 4/2 |  |  |  | COMPLETED | YES | 2025-03-31 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-03-31 18:16
MARCH-25 | MARCH-25 | NEW STORE | 3/31-Retail Ready |  |  | RECEIVED | 2025-03-12 | 1537 | 165484 | OK | FAST CONNECT INC | MRS.HUMAIRA SALEEM | 304 N Main St | Butler | PA | 16001 | BGC ID-366622494 | 1986-04-22 | 85-3352505 | 06-3337833 |  | firaa1975@gmail.com | 2025-02-27 |  | 2025-03-20 | LEASE | 2025-02-27 | 2025-02-17 | 2025-02-20 | COMPLETED | RECEIVED | 2025-03-05 | YES | APPROVED | 2025-03-10 |  |  |  | SUBMITTED | 2025-03-24 | 2025-03-27 | 2025-03-28 | 2025-04-28 | SUBMITTED |  | NOT REQUIRED |  | 2025-03-18 |  |  | ORDERED | ORDERED | COMPLETED | YES | 2025-03-31 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-04-01 07:23
MARCH-25 | MARCH-25 | NEW STORE | 3/29-Retail Ready |  |  | RECEIVED | 2025-03-13 | 1530 | 165470 | OK | KNV INC | MRS CHEUNG ANNIE | 327 W Marshall St | Norristown | PA | 19401 | BGC ID- 366654481 | 1978-09-12 | 47-4324870 | 02-1744014 |  | knvinc@icloud.com | 2025-02-26 |  | 2025-03-19 | LEASE | 2025-02-27 | 2025-02-25 | 2025-03-06 | COMPLETED | RECEIVED | 2025-03-07 | YES | APPROVED | 2025-03-08 | Old Tiles in Store Used | Old Tiles in Store Used | Old Tiles in Store Used | SUBMITTED | 2025-03-18 | 2025-03-24 | 2025-03-25 | 2025-03-21 | SUBMITTED |  | NOT REQUIRED |  | 2025-03-18 | Tracking #: PITT OHIO - 5050137754 - ETA 3/26 | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-03-29 | MARCH | RECEIVED | info@pinnaclemobility.com | 2025-03-29 16:02
APRIL-25 | APRIL-25 | NEW STORE | 4/23- Retail Ready |  |  | RECEIVED | 2025-03-20 | 1583 | 165568 | OK | Marsons Enterprise LLC | OMAR AKHTAR RAO | 34 New Kirk Plaza | BROOKLYN | NY | 11226 | BGC ID-355212349 | 1960-06-13 | 93-4532635 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-03-13 |  | 2025-04-10 | LEASE | 2025-03-13 | 2025-02-20 | 2025-03-08 | COMPLETED | RECEIVED | 2025-03-17 | YES | APPROVED | 2025-03-18 |  |  | EXCEPTION | SUBMITTED | 2025-04-14 | 2025-04-16 | 2025-04-17 | 2025-04-15 | SUBMITTED | 2025-04-11 | SUBMITTED | 2025-04-11 | 2025-04-10 | Tracking #: ESTES - 0285799594 - ETA | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-23 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-05-01 07:05
APRIL-25 | APRIL-25 | NEW STORE | 4/28- Retail Ready |  |  | RECEIVED | 2025-04-07 | 1659 | 165726 | OK | PINNACLE MOBILITY RETAIL INC | MR.CHRIS CHRISTOFOROU | 394 Utica Ave | BROOKLYN | NY | 11213 | BGC ID-365226260 | 1960-08-28 | 93-1565810 | 092-56-9344 | 516-297-4300 | info@pinnaclemobility.com | 2025-03-10 |  | 2025-04-11 | LEASE | 2025-04-04 | 2025-02-27 | 2025-03-07 | COMPLETED | RECEIVED | 2025-03-17 | YES | APPROVED | 2025-03-18 |  |  | EXCEPTION | SUBMITTED | 2025-04-15 | 2025-04-22 | 2025-04-23 |  | SUBMITTED | 2025-04-11 | SUBMITTED | 2025-04-11 | 2025-04-10 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-28 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-05-02 07:47
MARCH-25 | MARCH-25 | NEW STORE | 3/31-Retail Ready |  |  | RECEIVED | 2025-03-14 | 1510 | 165413 | OK | Horizon Handy Phone Systems Inc | MR.AYUB KHAN | 3451 Boston Rd | Bronx | NY | 10469 | BGC ID-346341817 | 1973-09-13 | 93-3849820 | 1078-64-867 |  | ayub244khan@gmail.com | 2025-03-05 |  | 2025-03-19 | LEASE | 2025-03-05 | 2025-02-27 | 2025-03-06 | COMPLETED | RECEIVED | 2025-03-07 | YES | APPROVED | 2025-03-08 |  |  |  | SUBMITTED | 2025-03-21 | 2025-03-26 | 2025-03-27 | 2025-03-24 | SUBMITTED |  | NOT REQUIRED |  | 2025-03-18 | Tracking #: ESTES - 0285805004 - ETA |  |  |  | COMPLETED | YES | 2025-03-31 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-03-31 18:17
MARCH-25 | MARCH-25 | NEW STORE | 3/31-Retail Ready |  |  | RECEIVED | 2025-03-13 | 1512 | 165415 | OK | TOTAL WIRELESS OF NEW ENGLAND INC | MRS.SYEDA ZUBDA NAQVI | 518 Park St | Hartford | CT | 06106 | BGC ID-361417375 | 1957-02-10 | 33-1610327 | 005-69-4525 |  | totalwirelessne@gmail.com | 2025-03-05 |  | 2025-03-20 | LEASE | 2025-03-06 | 2025-02-20 | 2025-03-01 | COMPLETED | RECEIVED | 2025-03-07 | YES | APPROVED | 2025-03-08 | 190690 | 548806 | 2025-03-06 | SUBMITTED | 2025-03-22 | 2025-03-26 | 2025-03-26 | 2025-04-28 | SUBMITTED |  | NOT REQUIRED |  | 2025-03-18 | Tracking #: ROADRUNNER - 645892068b - ETA | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-03-31 | MARCH | RECEIVED | gary@pinnaclemobility.com | 2025-04-01 07:24
APRIL-25 | APRIL-25 | NEW STORE | 4/30-Retail Ready |  |  | RECEIVED | 2025-03-20 | 1574 | 165542 | OK | JAC Mobile TX LLC | MR.ALMA ROSA CANO | 3620 SPRINGFIELD AVE | LAREDO | TX | 78040 | BGC ID-362970930 | 1983-04-26 | 33-1510420 |  | 956-771-0429 | jac.mobiletx@gmail.com | 2025-03-06 |  | 2025-04-14 | LEASE | 2025-03-06 | 2025-02-24 | 2025-02-28 | COMPLETED | RECEIVED | 2025-03-14 | YES | APPROVED | 2025-03-18 |  |  | EXCEPTION | SUBMITTED | 2025-04-22 | 2025-04-24 | 2025-04-28 | 2025-04-23 | SUBMITTED | 2025-04-09 | SUBMITTED | 2025-04-09 | 2025-04-10 | Tracking #: AAA COOPER - 662199116 - ETA | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-30 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-05-01 07:06
APRIL-25 | APRIL-25 | NEW STORE | 4/29- Retail Ready |  |  | RECEIVED | 2025-04-07 | 1628 | 165692 | OK | TOTAL WIRELESS OF FL INC | MRS.SYEDA ZUBDA NAQVI |  | Pompano Beach | FL | 33069 | BGC ID-361417375 | 1957-02-10 | 33-1661413 | 005-69-4525 | 516-813-8628 | totalwirelessne@gmail.com | 2025-03-27 |  |  | LEASE | 2025-03-27 | 2025-03-04 | 2025-03-10 | COMPLETED | RECEIVED | 2025-04-01 | NO | APPROVED | 2025-04-01 |  |  | Already have Tiles | SUBMITTED | 2025-04-23 | 2025-04-25 | 2025-04-25 | 2025-04-28 | SUBMITTED | 2025-04-24 | SUBMITTED | 2025-04-24 |  | Tracking #: TFORCE - 407927214 - ETA | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-29 | APRIL | RECEIVED | ops@pinnaclemobility.com | 2025-05-25 11:21
APRIL-25 | APRIL-25 | NEW STORE | 4/24- Retail Ready |  |  | RECEIVED | 2025-03-19 | 1577 | 165543 | OK | SUCCESS GROUP LLC | MRS.SHALINI KHURANA JAIN | 4728 S Broadway St | Wichita | KS | 67216 | BGC ID- 347825270 | 1979-08-02 | 93-4520322 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-03-07 |  |  | LEASE | 2025-03-07 | 2025-02-26 | 2025-03-05 | COMPLETED | RECEIVED | 2025-03-17 | YES | APPROVED | 2025-03-18 |  |  | EXCEPTION | SUBMITTED | 2025-04-05 | 2025-04-14 | 2025-04-17 | 2025-04-15 | SUBMITTED | 2025-04-07 | SUBMITTED | 2025-04-09 | 2025-04-10 | SUTTON - 210072329 - ETA 4/17 | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-24 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-04-24 10:07
APRIL-25 | APRIL-25 | NEW STORE | 4/24- Retail Ready |  |  | RECEIVED | 2025-03-19 | 1576 | 165544 | OK | SUCCESS GROUP LLC | MRS.SHALINI KHURANA JAIN | 2017 S Seneca St | Wichita | KS | 67213 | BGC ID- 347825270 | 1979-08-02 | 93-4520322 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-03-07 |  | 2025-04-09 | LEASE | 2025-03-07 | 2025-02-26 | 2025-03-05 | COMPLETED | RECEIVED | 2025-03-17 | YES | APPROVED | 2025-03-18 |  |  | EXCEPTION | SUBMITTED | 2025-04-05 | 2025-04-11 | 2025-04-15 | 2025-04-15 | SUBMITTED | 2025-04-07 | SUBMITTED | 2025-04-09 | 2025-04-10 | Tracking #: SUTTON - 210072330 - ETA 4/17 | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-24 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-04-24 11:10
APRIL-25 | APRIL-25 | NEW STORE | 4/30-Retail Ready |  |  | RECEIVED | 2025-04-15 | 1650 | 165785 | OK | FLASH WIRELESS INC | MR.AFZAL SHAIKH | 919 Coney Island Ave | Brooklyn | NY | 11230 | BGC ID-367786985 | 1954-01-05 | 33-3838374 | 767-50-7802 | 646-789-1600 | 919flashwireless@gmail.com | 2025-04-03 |  |  | LEASE | 2025-04-03 | 2025-03-21 | 2025-03-26 | COMPLETED | RECEIVED | 2025-04-08 | YES | APPROVED | 2025-04-09 |  |  | EXCEPTION | SUBMITTED | 2025-04-23 | 2025-05-28 | 2025-05-29 | 2025-04-28 | SUBMITTED | 2025-05-01 | SUBMITTED | 2025-05-01 | 2025-04-18 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-30 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-05-01 07:24
MAY-25 | MAY-25 | NEW STORE | 5/31-RETAIL READY | Install Date: 5/29/25 Fixture Delivery:5/27/25 12PM Estimated Retail Ready Date: 5/31/25 |  | RECEIVED | 2025-05-09 | 1765 | 165990 | OK | D MOBIL | MR.DANIEL MERCADO GENAO | 70-08 Forest ave | Ridgewood | NY | 11385 | BGC ID- 369071902 | 1977-07-02 | 27-2132256 | 102-98-7437 | 646-309-9648 | Danielmercado001@gmail.com | 2025-05-05 | NOT REQUIRED | 2025-05-16 | LEASE | 2025-05-05 | 2025-04-12 | 2025-04-16 | COMPLETED | RECEIVED | 2025-05-08 | NO | APPROVED | 2025-05-08 |  |  |  | SUBMITTED | 2025-05-22 | 2025-05-27 | 2025-05-29 | 2025-05-30 | SUBMITTED | 2025-05-13 | SUBMITTED | 2025-05-13 | 2025-05-21 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-05-31 | MAY | RECEIVED | ops@pinnaclemobility.com | 2025-06-05 10:06
APRIL-25 | APRIL-25 | NEW STORE | 4/30-Retail Ready |  |  | RECEIVED | 2025-04-15 | 1651 | 165823 | OK | TOTAL WIRELESS OF NEW ENGLAND INC | MRS.SYEDA ZUBDA NAQVI | 1055 Boston Post Rd | West Heaven | CT | 06516 | BGC ID-361417375 | 1957-02-10 | 33-1610327 | 005-69-4525 | 516-813-8628 | totalwirelessne@gmail.com | 2025-04-04 |  | 2025-04-18 | LEASE | 2025-03-26 | 2025-03-24 | 2025-04-04 | COMPLETED | RECEIVED | 2025-04-10 | YES | APPROVED | 2025-04-11 |  |  | EXCEPTION | SUBMITTED | 2025-04-21 | 2025-05-28 | 2025-05-28 |  | SUBMITTED | 2025-04-18 | SUBMITTED | 2025-04-18 | 2025-04-18 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-30 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-05-01 07:25
APRIL-25 | APRIL-25 | OWNERSHIP CHANGE | 4/28-Retail Ready |  |  | RECEIVED | 2025-03-31 | 0132 | 165648 | OK | HIGH SPEED WIRELESS CORP | MR.JUAN MIGUEL PEREZ MEDINA | 1704 BERGENLINE AVE | UNION CITY | NJ | 07087 | BGC ID- 367195731 | 1986-12-04 | 33-4061924 | 767-50-7802 | 646-730-8794 | highspeedwireless0@gmail.com | 2025-03-25 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [5 empty] | NOT REQUIRED | NOT REQUIRED | PENDING | PENDING | COMPLETED | YES | 2025-04-28 | APRIL | RECEIVED | ops@pinnaclemobility.com | 2025-05-30 07:06
APRIL-25 | APRIL-25 | NEW STORE | 4/30-Retail Ready |  |  | RECEIVED | 2025-04-15 | 1653 | 165825 | OK | LIMRA COMMUNICATIONS | MR.FARHAN UMAR SHAIKH | 555 Almeda Mall | Houston | TX | 77075 | BGC ID-367582226 | 1975-06-11 | 85-2929012 | 219-417-081 | 832-298-0160 | limra.communications2318@gmail.com | 2025-04-01 |  |  | LEASE | 2025-03-31 | 2025-03-24 | 2025-03-27 | COMPLETED | RECEIVED | 2025-04-10 | YES | APPROVED | 2025-04-11 |  |  | EXCEPTION | SUBMITTED | 2025-04-23 | 2025-04-28 | 2025-04-28 | 2025-04-28 | SUBMITTED | 2025-04-24 | SUBMITTED | 2025-04-24 | 2025-04-18 |  | PENDING | PENDING | PENDING | COMPLETED | YES | 2025-04-30 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-04-30 15:42
APRIL-25 | APRIL-25 | NEW STORE | 4/29- Retail Ready |  |  | RECEIVED | 2025-04-09 | 1673 | 165731 | OK | ALON MARS NETWORK INC | MR.GHULAM MUSTAFA ALI | 46 Gramatan Ave | Mt. Vernon | NY | 10550 | BGC ID-366221374 | 1998-02-19 | 33-3341659 | 140-04-8360 | 215-778-8655 | alonmarsnetwork@gmail.com | 2025-04-04 |  | 2025-04-09 | LEASE | 2025-04-08 | 2025-03-27 | 2025-04-01 | COMPLETED | RECEIVED | 2025-04-08 | YES | APPROVED | 2025-04-08 |  |  | EXCEPTION | SUBMITTED | 2025-04-17 | 2025-04-24 | 2025-04-28 | 2025-04-21 | SUBMITTED | 2025-04-11 | SUBMITTED | 2025-04-11 | 2025-04-10 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-29 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-05-01 07:06
APRIL-25 | APRIL-25 | NEW STORE | 4/30-Retail Ready |  |  | RECEIVED | 2025-04-18 | 1648 | 165781 | OK | SUCCESS GROUP LLC | MRS.SHALINI KHURANA JAIN | 4034 S 24th St | Omaha | NE | 68107 | BGC ID- 347825270 | 1979-08-02 | 93-4520322 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-04-01 |  | 2025-04-17 | LEASE | 2025-04-01 | 2025-02-26 | 2025-03-06 | COMPLETED | RECEIVED | 2025-04-11 | YES | APPROVED | 2025-04-12 |  |  | EXCEPTION | SUBMITTED | 2025-04-21 | 2025-04-25 | 2025-04-26 | 2025-04-22 | SUBMITTED | 2025-04-18 | SUBMITTED | 2025-04-18 | 2025-04-18 | Tracking #: MAGNAM - 7458702 - DEL 4/29 | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-30 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-04-30 14:49
JULY-25 | JULY-25 | NEW STORE |  |  | 4/21/25-alfacom and spectrio mail | RECEIVED | 2025-04-15 | 1649 | 165838 | OK | JAC Mobile TX LLC | MR.ALMA ROSA CANO | 211 Jefferson | Eagle Pass | TX | 78852 | BGC ID-362970930 | 1983-04-26 | 33-1510420 | 677-40-9638 | 956-771-0429 | jac.mobiletx@gmail.com | 2025-03-27 | NOT REQUIRED |  | LEASE | 2025-03-27 | 2025-03-14 | 2025-03-19 | COMPLETED | RECEIVED | 2025-04-10 | YES | APPROVED | 2025-04-11 |  |  | Already have Tiles | [5 empty] | SUBMITTED | 2025-04-21 | SUBMITTED | 2025-04-21 | 2025-05-21 | [9 empty] | ops@pinnaclemobility.com | 2025-06-05 10:06
MAY-25 | MAY-25 | NEW STORE | 5/29-RETAIL READY | Install Date: 5/16/25 Fixture Delivery: 5/15/25 8 AM Estimated Retail Ready Date: 5/18/25 |  | RECEIVED | 2025-05-05 | 1608 | 165813 | OK | TOTAL WIRELESS OF NEW ENGLAND INC | MRS.SYEDA ZUBDA NAQVI | 1291 Albany Ave | Hartford | CT | 06112 | BGC ID-361417375 | 1957-02-10 | 33-1610327 | 005-69-4525 | 516-813-8628 | totalwirelessne@gmail.com | 2025-04-09 | NOT REQUIRED | 2025-05-21 | LEASE | 2025-03-26 | 2025-04-05 | 2025-04-08 | COMPLETED | RECEIVED | 2025-04-22 | YES | APPROVED | 2025-04-30 |  |  |  | SUBMITTED | 2025-05-02 | 2025-05-15 | 2025-05-16 |  | SUBMITTED | 2025-05-13 | SUBMITTED | 2025-05-13 | 2025-04-18 |  | PENDING | PENDING | PENDING | COMPLETED | YES | 2025-05-29 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-05-31 15:42
APRIL-25 | APRIL-25 | NEW STORE | 4/30-Retail Ready |  |  | RECEIVED | 2025-04-15 | 1652 | 165824 | OK | SUCCESS GROUP LLC | MRS.SHALINI KHURANA JAIN | 4121 S 84th St | Omaha | NE | 68127 | BGC ID- 347825270 | 1979-08-02 | 93-4520322 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-04-04 |  |  | LEASE | 2025-04-04 | 2025-03-29 | 2025-04-02 | COMPLETED | RECEIVED | 2025-04-10 | YES | APPROVED | 2025-04-11 |  |  | EXCEPTION | SUBMITTED | 2025-04-23 | 2025-04-26 | 2025-04-30 | 2025-04-28 | SUBMITTED | 2025-04-18 | SUBMITTED | 2025-04-18 | 2025-04-18 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-04-30 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-05-05 09:52
JULY-25 | JULY-25 | NEW STORE | 5/5-Application Will Be sent Today, Permit Required open in June | 4/24 lease will be received | pending docusign | RECEIVED | 2025-06-05 |  |  |  | KARAMA CONNECT TEXAS LLC | MR.UTPAL RASTOGI | 1111 W Airport Freeway, Suite 151 | Irving | TX | 75062 | BGC ID- 366253754 | 1973-10-12 | 33-3127794 | 609-25-3063 | 916-388-4811 | karamaconnecttx@gmail.com | 2025-05-06 | REQUIRED |  |  |  | 2025-03-29 | 2025-04-02 | COMPLETED | RECEIVED | 2025-05-20 |  | APPROVED | 2025-06-03 | [8 empty] | PENDING |  | PENDING | [11 empty] | gary@pinnaclemobility.com | 2025-06-06 10:26
MAY-25 | MAY-25 | NEW STORE | 5/29-RETAIL READY | Install Date: 5/20/25 Fixture Delivery: 5/20/25 7 AM Estimated Retail Ready Date: 5/22/25 |  | RECEIVED | 2025-05-05 | 1761 | 165981 | OK | PSL Wireless LLC | MS.ANASTACIA KATE HUSSAIN | 938 Market St | San Francisco | CA | 94102 | BGC ID -366782010 | 1996-09-26 | 33-3374566 | 658-56-9512 | 346-317-4326 | totalwirelessbypsl@gmail.com | 2025-04-10 | NOT REQUIRED | 2025-05-07 | LEASE | 2025-04-10 | 2025-04-03 | 2025-04-08 | COMPLETED | RECEIVED | 2025-04-17 | YES | APPROVED | 2025-05-05 |  |  |  | SUBMITTED | 2025-05-10 | 2025-05-20 | 2025-05-20 | 2025-05-19 | SUBMITTED | 2025-05-07 | SUBMITTED | 2025-05-07 | 2025-05-21 |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-05-29 | MAY | RECEIVED | ops@pinnaclemobility.com | 2025-06-05 10:06
JUNE-25 | JUNE-25 | NEW STORE |  | 6/6- merchant Agreement Pending |  | RECEIVED | 2025-04-23 | 1681 | 165836 |  | KARAMA CONNECT TEXAS LLC | MR.UTPAL RASTOGI | 1816 W Irving Blvd | Irving | TX | 75061 | BGC ID- 366253754 | 1973-10-12 | 33-3127794 | 609-25-3063 | 916-388-4811 | karamaconnecttx@gmail.com | 2025-04-08 | REQUIRED |  | LEASE | 2025-04-07 | 2025-02-18 | 2025-02-18 | COMPLETED | RECEIVED | 2025-04-15 | NO | APPROVED | 2025-04-15 | [8 empty] | PENDING |  | PENDING | [11 empty] | gary@pinnaclemobility.com | 2025-06-06 11:05
MAY-25 | MAY-25 | NEW STORE | 5/31-RETAIL READY | Install Date: 5/26/25 Fixture Delivery: 5/22/25 Estimated Retail Ready Date: 5/28/25 |  | RECEIVED | 2025-05-12 | 1764 | 166063 | OK | PAK WIRELESS LIMITED | MR.TAUQEER DAAR | 1881 A Rockaway Parkway | Brooklyn | NY | 11236 | BGC ID- 368995996 | 1981-02-20 | 33-4801612 | 089-61-5302 | 212-470-0159 | Pakwirelesslimited@gmail.com | 2025-05-05 | NOT REQUIRED | 2025-05-14 | LEASE | 2025-04-30 | 2025-04-11 | 2025-04-25 | COMPLETED | RECEIVED | 2025-05-09 | YES | APPROVED | 2025-05-12 |  |  |  | SUBMITTED | 2025-05-19 | 2025-05-22 | 2025-05-26 | 2025-05-27 | SUBMITTED | 2025-05-16 | SUBMITTED | 2025-05-16 | 2025-05-21 | Received | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-05-31 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-05-31 12:31
MAY-25 | MAY-25 | OWNERSHIP CHANGE | 5/13-RETAIL READY |  |  | NOT REQUIRED | NOT REQUIRED | 0800 | 165865 | OK | Infinitytel Inc | MR.KAVLEEN S KOHLI | 1271 SUNRISE HWY | COPIAGUE | NY | 11726 | BGC ID-360656991 | 1979-12-13 | 33-1395369 | 088-88-7902 | 347-248-6415 | twcopiague@gmail.com | 2025-04-17 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-04-29 | SUBMITTED | 2025-04-29 | 2025-04-28 | Not required | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-05-13 | MAY | RECEIVED | ops@pinnaclemobility.com | 2025-05-30 07:06
JUNE-25 | JUNE-25 | NEW STORE |  | 5/7- Floor Plan received Distributor approval pending |  | RECEIVED | 2025-06-05 | 1751 | 166036 |  | SUCCESS GROUP LLC | MRS.SHALINI KHURANA JAIN | 4301 E 50th Terrace | Kansas City | MO | 63140 | BGC ID- 347825270 | 1979-08-02 | 93-4520322 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-04-30 | NOT REQUIRED |  | LEASE | 2025-04-27 | 2025-04-01 | 2025-04-07 | COMPLETED | RECEIVED | 2025-05-07 |  | APPROVED | 2025-06-03 | [22 empty] | gary@pinnaclemobility.com | 2025-06-06 11:05
MAY-25 | MAY-25 | OWNERSHIP CHANGE | 5/22-RETAIL READY |  |  | NOT REQUIRED | NOT REQUIRED | 0647 | 165852 | OK | AMA GROUP NY LLC | MRS.SHALINI KHURANA JAIN | 442 BLUE HILL AVE | DORCHESTER | MA | 02121 | BGC ID- 347825270 | 1979-08-02 | 33-2099299 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-04-17 |  | 2025-04-24 | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-04-29 | SUBMITTED |  | 2025-05-21 | [5 empty] | YES | 2025-05-22 | MAY | RECEIVED | ops@pinnaclemobility.com | 2025-06-05 10:06
MAY-25 | MAY-25 | OWNERSHIP CHANGE | 5/22-RETAIL READY |  |  | NOT REQUIRED | NOT REQUIRED | 0859 | 165853 | OK | AMA GROUP NY LLC | MRS.SHALINI KHURANA JAIN | 593 WASHINGTON ST | DORCHESTER | MA | 02124 | BGC ID- 347825270 | 1979-08-02 | 33-2099299 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-04-17 |  | 2025-04-24 | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-04-29 | SUBMITTED |  | 2025-05-21 | [5 empty] | YES | 2025-05-22 | MAY | RECEIVED | ops@pinnaclemobility.com | 2025-06-05 10:06
MAY-25 | MAY-25 | OWNERSHIP CHANGE | 5/22-RETAIL READY |  |  | NOT REQUIRED | NOT REQUIRED | 1133 | 165854 | OK | AMA GROUP NY LLC | MRS.SHALINI KHURANA JAIN | 396 Broadway | Chelsea | MA | 02150 | BGC ID- 347825270 | 1979-08-02 | 33-2099299 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-04-17 |  | 2025-04-24 | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-04-29 | SUBMITTED | [7 empty] | YES | 2025-05-22 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-06-04 08:19
APRIL-25 | APRIL-25 | OWNERSHIP CHANGE | 4/30-Retail Ready |  |  | NOT REQUIRED | NOT REQUIRED | 1160 | 165850 | OK | HND WIRELESS LLC | MR.HARIS AMJAD | 20516 Linden Blvd | Jamaica | NY | 11412 | BGC ID- 339632683 | 1995-10-02 | 92-2722435 | 677-40-9638 | 212-470-9272 | harisamjad3809@gmail.com | 2025-04-16 |  | 2025-04-24 | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-04-29 | SUBMITTED | [8 empty] | 2025-04-30 | APRIL | RECEIVED | gary@pinnaclemobility.com | 2025-05-02 13:30
MAY-25 | MAY-25 | NEW STORE | 5/31-RETAIL READY | Install Date: 5/31/25 Fixture Delivery: 5/30/25 8 AM Estimated Retail Ready Date: 5/31/25 |  | RECEIVED | 2025-05-14 | 1780 | 166045 | OK | DIGITAL UPNY INC | MR. KULWANT SINGH | 2284 Lyell Ave STE-2 | Rochester | NY | 14606 | BGC ID-360428585 | 1990-02-02 | 99-4960986 | 817-75-0758 | 585-500-0002 | digitalupny@gmail.com | 2025-04-29 | NOT REQUIRED | 2025-05-19 | LEASE | 2025-05-07 | 2025-04-01 | 2025-04-19 | COMPLETED | RECEIVED | 2025-05-12 | NO | APPROVED | 2025-05-13 |  |  |  | SUBMITTED | 2025-05-24 |  |  |  | SUBMITTED | 2025-05-15 | SUBMITTED | 2025-05-15 |  |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-05-31 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-05-31 15:53
MAY-25 | MAY-25 | NEW STORE | 5/31-RETAIL READY | Install Date: 5/30/25 Fixture Delivery: 5/29/25 8 AM Estimated Retail Ready Date: 5/30/25 |  | RECEIVED | 2025-05-16 | 1805 | 166183 | OK | INTERTECH WIRELESS CORP | MR.HATEM ATTIA MOHAMED | 4409 Ave D | BROOKLYN | NY | 11203 | BGC ID-369250610 | 1976-12-07 | 33-4957705 | 374-63-6983 | 347-933-7866 | mohatemattia@gmail.com | 2025-05-09 |  |  | LEASE | 2025-05-15 | 2025-04-21 | 2025-04-24 | COMPLETED | RECEIVED | 2025-05-14 |  | APPROVED | 2025-05-15 |  |  |  | SUBMITTED | 2025-05-23 | 2025-05-29 | 2025-05-30 |  | SUBMITTED | 2025-05-22 | SUBMITTED | 2025-05-22 |  |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-05-31 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-06-05 09:34
MAY-25 | MAY-25 | NEW STORE | 5/31-RETAIL READY | Install Date: 5/29/25 Fixture Delivery: 5/28/25 8 AM Estimated Retail Ready Date: 5/30/25 | docusign spectrio and alfacoomm mailed | RECEIVED | 2025-05-16 | 1804 | 166159 | OK | AZ WIRELESS INC | MR.AYUB KHAN | 3041-3135 Mechanicsville Tpke – (Oak Hill Plaza) | Richmond | VA | 23223 | BGC ID-346341817 | 1973-09-13 | 33-5011356 | 1078-64-867 | 929-235-4055 | ayub244khan@gmail.com | 2025-05-08 |  | 2025-05-27 | LEASE | 2025-05-15 | 2025-04-21 | 2025-04-25 | COMPLETED | RECEIVED | 2025-05-14 |  | APPROVED | 2025-05-15 |  |  |  | SUBMITTED | 2025-05-22 | 2025-05-28 | 2025-05-29 |  | SUBMITTED |  | SUBMITTED | [7 empty] | YES | 2025-05-31 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-06-02 07:40
MAY-25 | MAY-25 | NEW STORE | 5/31-RETAIL READY | Install Date: 5/29/25 Fixture Delivery: 5/29/25 7 AM Estimated Retail Ready Date: 5/30/25 | 5/15-spectrio and alfacomm mailed | RECEIVED | 2025-05-14 | 1786 | 166043 | OK | PINNACLE MOBILITY RETAIL INC | MR.CHRIS CHRISTOFOROU | 831 Bowman St | Lebanon | PA | 17046 | BGC ID-365226260 | 1960-08-28 | 93-1565810 | 092-56-9344 | 516-297-4300 | info@pinnaclemobility.com | 2025-05-07 |  |  | LEASE | 2025-05-01 | 2025-04-28 | 2025-05-05 | COMPLETED | RECEIVED | 2025-05-12 | YES | APPROVED | 2025-05-14 |  |  |  | SUBMITTED | 2025-05-22 | 2025-05-29 | 2025-05-29 | 2025-05-28 | SUBMITTED | 2025-05-15 | SUBMITTED | 2025-05-15 | [6 empty] | YES | 2025-05-31 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-06-02 07:34
MAY-25 | MAY-25 | NEW STORE | 5/31-RETAIL READY | Install Date: 5/29/25 Fixture Delivery: 5/29/25 7 AM Estimated Retail Ready Date: 5/30/25 |  | RECEIVED | 2025-05-16 | 1794 | 166060 | OK | TOTAL WIRELESS OF WIRELESS FL INC | MRS.SYEDA ZUBDA NAQVI | 19902 B NW 2nd Ave | Miami | FL | 33169 | BGC ID-361417375 | 1957-02-10 | 33-1661413 | 005-69-4525 | 516-813-8628 | totalwirelessne@gmail.com | 2025-05-07 |  | 2025-05-14 | LEASE | 2025-05-12 | 2025-04-30 | 2025-05-06 | COMPLETED | RECEIVED | 2025-05-14 |  | APPROVED | 2025-05-15 |  |  |  | SUBMITTED | 2025-05-22 | 2025-05-29 | 2025-05-29 | 2025-05-27 | SUBMITTED | 2025-05-16 | SUBMITTED | 2025-05-16 |  | Not received | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-05-31 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-05-31 12:31
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/19- Documents Submitted to Onboarding | docusign spectrio and alfacoomm mailed | RECEIVED | 2025-04-30 | 0095 | 166006 | OK | LUCKY STAR 777 INC | MRS.CHETNA PURSHOTAMANI | 1701 SUNRISE HWY | BAY SHORE | NY | 11706 | BGC ID-368924992 | 1971-01-02 | 99-3592512 | 580-35-0465 | 929-623-3989 | twbayshore@gmail.com | 2025-04-30 | NOT REQUIRED | 2025-05-19 | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-05-26 | SUBMITTED | 2025-05-26 | [10 empty] | gary@pinnaclemobility.com | 2025-06-05 09:23
MAY-25 | MAY-25 | NEW STORE | 5/31-RETAIL READY | Install Date: 5/30/25 Fixture Delivery: 5/28/25 8 AM Estimated Retail Ready Date: 5/30/25 | submitted spectrio and alfacoomm | RECEIVED | 2025-05-16 | 1793 | 166068 | OK | HND WIRELESS LLC | MR.HARIS AMJAD | 3206 Church Ave | Brooklyn | NY | 11226 | BGC ID- 339632683 | 1995-10-02 | 92-2722435 | 677-40-9638 | 212-470-9272 | harisamjad3809@gmail.com | 2025-05-07 |  | 2025-05-13 | LEASE | 2025-05-07 | 2025-04-30 | 2025-05-09 | COMPLETED | RECEIVED | 2025-05-15 |  | APPROVED | 2025-05-15 |  |  |  | SUBMITTED | 2025-05-22 | 2025-05-28 | 2025-05-30 | 2025-05-27 | SUBMITTED | 2025-05-20 | SUBMITTED | 2025-05-20 |  |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-05-31 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-05-31 16:16
MAY-25 | MAY-25 | NEW STORE | 5/31-RETAIL READY | Install Date: 5/27/25 Fixture Delivery: 5/23/25 8 AM Estimated Retail Ready Date: 5/29/25 | 5/15-spectrio and alfacomm mailed |  |  | 1784 | 166046 | OK | PINNACLE MOBILITY RETAIL INC | MR.CHRIS CHRISTOFOROU | 474 Hempstead Turnpike | Elmont | NY | 11003 | BGC ID-365226260 | 1960-08-28 | 93-1565810 | 092-56-9344 | 516-297-4300 | info@pinnaclemobility.com | 2025-05-02 | NOT REQUIRED | 2025-05-21 | LEASE | 2025-05-08 | 2025-04-23 | 2025-04-28 | COMPLETED | RECEIVED | 2025-05-09 | NO | APPROVED | 2025-05-12 |  |  |  | SUBMITTED | 2025-05-21 | 2025-05-23 | 2025-05-27 | 2025-05-28 | SUBMITTED | 2025-05-15 | SUBMITTED | 2025-05-15 |  |  | ORDERED | ORDERED | ORDERED | COMPLETED | YES | 2025-05-31 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-05-31 15:42
JULY-25 | JULY-25 | NEW STORE |  | 5/8- Application sent to vanessa, Lease Pending | docusign spectrio and alfacoomm recived | [5 empty] | AZ WIRELESS INC | MR.AYUB KHAN | 5206-5246 Chamberlayne Rd - (Brookhill Azalea) | Richmond | VA | 23227 | BGC ID-346341817 | 1973-09-13 | 33-5011356 | 1078-64-867 | 929-235-4055 | ayub244khan@gmail.com | 2025-05-08 |  |  |  |  | 2025-04-18 | 2025-04-23 | COMPLETED | RECEIVED | 2025-05-14 |  | PENDING | [9 empty] | RECEIVED BUT NOT SUBMITTED |  | RECEIVED BUT NOT SUBMITTED | [11 empty] | gary@pinnaclemobility.com | 2025-06-03 12:31
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE | 6/4-RETAIL READY | 5/7-Application Submitted for OC at Smartsheet | 6/5-Dcousign recieved agreement for sno parker singh | RECEIVED | 2025-05-08 | 0067 | 166152 | OK | B WIRELESS INC | MR.SNO PARKER SINGH | 13520 LIBERTY AVE | SOUTH RICHMOND HILL | NY | 11419 | BGC ID-369185875 | 1988-11-26 | 61-1959836 | 1239-89-400 | 929-232-0002 | bwireless009@gmail.com | 2025-05-07 |  | 2025-05-27 | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | PENDING |  | PENDING | [7 empty] | YES | 2025-06-04 | MAY | RECEIVED | gary@pinnaclemobility.com | 2025-06-05 09:23
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  |  | submitted spectrio and alfacoomm | RECEIVED | 2025-05-14 | 0073 | 166220 | OK | SKKY BUY LLC | MR.TAYEFUR REHMAN | 125 ROCKAWAY AVE | VALLEY STREAM | NY | 11580 | BGC ID-369371622 | 1995-05-24 | 85-2914676 | 7093-97-956 | 917-400-3849 | skky.totalwireless@gmail.com | 2025-05-09 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-05-20 | SUBMITTED | 2025-05-20 | [10 empty] | gary@pinnaclemobility.com | 2025-06-05 09:38
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/13- Application Submitted |  | RECEIVED | 2025-05-13 | 1230 | 166150 | OK | JSS SERVICES CORP | MR.ABHIJAT BHASIN | 219 E GOODNIGHT AVE | ARANSAS PASS | TX | 78336 | BGC ID-369371622 | 1975-09-10 | 39-2090696 | 223497071 | 804-385-0452 | bhasinabi@gmail.com | 2025-05-13 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-05-26 | SUBMITTED | 2025-05-26 | [10 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/13- Application Submitted |  | RECEIVED | 2025-05-13 | 1229 | 166151 | OK | JSS SERVICES CORP | MR.ABHIJAT BHASIN | 1216 Waldron Rd | Corpus Christi | TX | 78418 | BGC ID-369371622 | 1975-09-10 | 39-2090696 | 223497071 | 804-385-0452 | bhasinabi@gmail.com | 2025-05-13 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-05-26 | SUBMITTED | 2025-05-26 | [10 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/13- Application Submitted |  | RECEIVED | 2025-05-13 | 1228 | 166149 | OK | JSS SERVICES CORP | MR.ABHIJAT BHASIN | 11101 LEOPARD ST STE 5 | Corpus Christi | TX | 78410 | BGC ID-369371622 | 1975-09-10 | 39-2090696 | 223497071 | 804-385-0452 | bhasinabi@gmail.com | 2025-05-13 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-05-26 | SUBMITTED | 2025-05-26 | [10 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/13- Application Submitted |  | RECEIVED | 2025-05-13 | 1333 | 166148 | OK | JSS SERVICES CORP | MR.ABHIJAT BHASIN | 3519 S STAPLES ST | CORPUS CHRISTI | TX | 78411 | BGC ID-369371622 | 1975-09-10 | 39-2090696 | 223497071 | 804-385-0452 | bhasinabi@gmail.com | 2025-05-13 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-05-26 | SUBMITTED | 2025-05-26 | [10 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/13- Application Submitted |  | RECEIVED | 2025-05-13 | 1508 | 166147 | OK | JSS SERVICES CORP | MR.ABHIJAT BHASIN | 725 S 14th St | Kingsville | TX | 78363 | BGC ID-369371622 | 1975-09-10 | 39-2090696 | 223497071 | 804-385-0452 | bhasinabi@gmail.com | 2025-05-13 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-05-26 | SUBMITTED | 2025-05-26 | [10 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/14-Application Submitted | docusign spectrio and alfacoomm mailed |  |  | 0113 | 166200 | OK | COBRA WIRELESS INC | MS. FARAH SHAHBAZ | 1573 DUTCH BROADWAY | VALLEY STREAM | NY | 11580 | BGC ID-369434587 | 1977-09-30 | 39-2083702 | 075-96-2662 | 917-847-1350 | cobrawireless1573@yahoo.com | 2025-05-14 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | SUBMITTED | 2025-05-23 | SUBMITTED | 2025-05-26 | [10 empty] | gary@pinnaclemobility.com | 2025-06-05 09:37
JUNE-25 | JUNE-25 | NEW STORE |  | 6/6- Executed Lease Sent to Vanessa | [6 empty] | HND WIRELESS LLC | MR.HARIS AMJAD | 582 Livonia Ave | Brooklyn | NY | 11207 | BGC ID- 339632683 | 1995-10-02 | 92-2722435 | 677-40-9638 | 212-470-9272 | harisamjad3809@gmail.com | 2025-05-20 |  |  | LEASE | 2025-06-06 | 2025-05-06 | 2025-05-06 | COMPLETED | RECEIVED | 2025-05-27 | YES | APPROVED | 2025-05-28 | [22 empty] | gary@pinnaclemobility.com | 2025-06-06 12:45
JULY-25 | JULY-25 | NEW STORE |  | 5/16- Application Submitted | [6 empty] | TOTAL WIRELESS OF NEW ENGLAND INC | MRS.SYEDA ZUBDA NAQVI | 641 Farmington Ave, (Bristol Plaza) | Briston | CT | 06010 | BGC ID-361417375 | 1957-02-10 | 33-1610327 | 005-69-4525 | 516-813-8628 | totalwirelessne@gmail.com | 2025-05-16 |  |  |  |  | Not required | Not Required | COMPLETED | RECEIVED | 2025-05-23 | [25 empty] | gary@pinnaclemobility.com | 2025-06-03 12:34
JUNE-25 | JUNE-25 | NEW STORE |  | 6/5- Waiting for fixture |  | RECEIVED | 2025-05-30 | 1824 | 166211 |  | SUCCESS GROUP LLC | MRS.SHALINI KHURANA JAIN | 7815 E Harry St | Wichita | KS | 67207 | BGC ID- 347825270 | 1979-08-02 | 93-4520322 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-05-19 |  |  | LEASE | 2025-05-19 | 2025-04-29 | 2025-05-05 | COMPLETED | RECEIVED | 2025-05-27 | YES | APPROVED | 2025-06-27 |  |  |  | SUBMITTED | 2025-06-05 | [17 empty] | gary@pinnaclemobility.com | 2025-06-05 11:47
AUGUST-25 | AUGUST-25 | NEW STORE |  |  | docusign spectrio and alfacoomm recived | [5 empty] | AZ WIRELESS INC | MR.AYUB KHAN | 7103 Staples Mill Rd | Richmond | VA | 23228 | BGC ID-346341817 | 1973-09-13 | 33-5011356 | 1078-64-867 | 929-235-4055 | ayub244khan@gmail.com | 2025-05-22 |  |  |  |  | 2025-04-23 | 2025-04-29 | COMPLETED | RECEIVED | 2025-05-30 | [11 empty] | RECEIVED BUT NOT SUBMITTED |  | RECEIVED BUT NOT SUBMITTED | [11 empty] | gary@pinnaclemobility.com | 2025-06-03 12:42
JUNE-25 | JUNE-25 | NEW STORE | [5 empty] | 1835 | 166244 |  | TOTAL WIRELESS OF NEW ENGLAND INC | MRS.SYEDA ZUBDA NAQVI | 1635 Warwick Ave, Gateway Shopping Center | Warwick | RI | 02889 | BGC ID-361417375 | 1957-02-10 | 33-1610327 | 005-69-4525 |  | totalwirelessne@gmail.com | 2025-05-22 |  |  |  |  | 2025-05-05 | 2025-05-12 | COMPLETED | RECEIVED | 2025-05-30 | YES | APPROVED | 2025-06-03 | [22 empty] | gary@pinnaclemobility.com | 2025-06-05 13:20
JUNE-25 | JUNE-25 | NEW STORE | [8 empty] | DIGITAL UPNY INC | MR. KULWANT SINGH | 1135 Culver Rd | Rochester | NY | 14609 | BGC ID-360428585 | 1990-02-02 | 99-4960986 | 817-75-0758 | 585-500-0002 | digitalupny@gmail.com | 2025-05-23 |  |  | LEASE | 2025-06-03 | 2025-05-15 | 2025-05-19 | COMPLETED | PENDING |  |  | PENDING | [23 empty] | gary@pinnaclemobility.com | 2025-06-05 11:34
JUNE-25 | JUNE-25 | NEW STORE |  | 6/5-Application Send to Vanessa | 6/4- Application Send to Dealer for Signature | [5 empty] | NEXWAVE WIRELESS | MS.ANTOINETTE SHAVONNE MAEBANE | 617 West Lake Street | Minneapolis | MN | 55408 | BGC ID-369100463 | 1993-12-08 | 33-4675735 |  | 612-261-9032 | nexwavewireless@gmail.com | 2025-06-05 |  |  | LEASE | 2025-06-05 | 2025-05-27 | 2025-06-03 | COMPLETED | PENDING |  |  | PENDING | [23 empty] | gary@pinnaclemobility.com | 2025-06-05 11:47
JUNE-25 | JULY-25 | NEW STORE |  | 6/4-Application Sent to Dealer for Sign off | [6 empty] | JBAN SERVICES CORP | MR.ABHIJAT BHASIN | 129 South Parker Street | Olathe | KS | 66061 | BGC ID-369371622 | 1975-09-10 | 39-2480387 | 223497071 | 804-385-0452 | bhasinabi@gmail.com | 2025-06-04 |  |  |  |  | 2025-05-19 | 2025-05-23 | COMPLETED | PENDING |  |  | PENDING | [23 empty] | gary@pinnaclemobility.com | 2025-06-05 11:34
JULY-25 | JULY-25 | NEW STORE | [10 empty] | 3202 S Belt Hwy | St. Joseph | MO | 64503 | [41 empty] | gary@pinnaclemobility.com | 2025-06-03 12:39
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/28-Application Submitted to Lisa |  |  |  | 1786 | 166291 | OK | MARSONS ENTERPRISE LLC | MR.OMAR AKHTAR RAO | 831 Bowman St | Lebanon | PA | 17046 | BGC ID-355212349 | 1960-06-13 | 93-4532635 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-05-28 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 14:26
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/28-Application Submitted to Lisa |  | RECEIVED | 2025-06-02 | 1560 | 166252 |  | Y2K ENTERPRISE, INC | MR.JOON YOUNG KIM | 7102 Hull Street Rd | North Chesterfield | VA | 23235 |  | 1975-07-13 | 37-2148662 | 592-02-2038 | 703-750-0137 | totalbyy2k@gmail.com | 2025-05-28 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/27- Documents Sent to JOON YOUNG KIM for sign off |  | RECEIVED | 2025-06-02 | 1072 | 163102 | OK | Y2K ENTERPRISE, INC | MR.JOON YOUNG KIM | 6531 Little River Tpke | Alexandria | VA | 22312 |  | 1975-07-13 | 37-2148662 | 592-02-2038 | 703-750-0137 | totalbyy2k@gmail.com | 2025-05-28 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-06 10:55
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  |  |  | RECEIVED | 2025-06-03 | 1075 | 163121 | OK | TOTAL TALK WHEATON INC | MR.MADHUR NARANG | 2575 Ennalls Ave | Silver Spring | MD | 20902 |  | 1993-04-30 | 99-3578702 | 805-41-4983 | 301-933-3849 | skwireless100@gmail.com | 2025-05-30 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-06 10:55
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/28-Application Submitted to Lisa |  | RECEIVED | 2025-06-02 | 1098 | 163373 | OK | ALL WIRELESS INC | MR.MIN HO LEE | 11750 Business Park Dr, STE 101 | Waldorf | MD | 20601 |  | 1972-08-17 | 35-2827379 | 674-20-7933 | 443-326-5700 | allwireless5692@gmail.com | 2025-05-28 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-06 10:58
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  |  |  | RECEIVED | 2025-06-03 | 1067 | 163078 | OK | TOTAL TALK | MRS.JASPREET KAUR | 11000 Baltimore Ave | Beltsville | MD | 20705 |  | 1987-09-20 | 99-3766948 | 686-34-0059 | 240-790-8470 | preet.totaltalk@gmail.com | 2025-05-30 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE | [5 empty] | 1064 |  |  | SR WIRELESS 1 | MR.IGOR BUDIYANSKIY | 1310 Homestead Rd N | Lehigh Acres | FL | 33936 |  | 1988-05-04 | 99-3973476 | 051-88-4034 | 239-491-2442 | igor.b@vzwair.com | 2025-06-06 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-06 10:54
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/28-Application Submitted to Lisa |  |  |  | 1175 | 164042 | OK | ADAM WIRELESS | MR.SADEK ABDEL AZIZ | 1001 N Miami Blvd | Durham | NC | 27703 |  | 1986-08-03 | 99-4999830 | 085-76-6706 | 919-908-0123 | alex@adamwirelessinc.com | 2025-05-28 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-06 10:59
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/28-Application Submitted to Lisa |  | RECEIVED | 2025-06-02 | 1219 | 164157 | OK | ALL WIRELESS INC | MR.MIN HO LEE | 1056 Elden St | Herndon | VA | 20170 |  | 1972-08-17 | 35-2827379 | 674-20-7933 | 443-326-5700 | allwireless5692@gmail.com | 2025-05-28 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/28-Application Submitted to Lisa |  |  |  | 1269 | 166255 | OK | AZ WIRELESS INC | MR.AYUB KHAN | 649 Newtown Rd | Virginia Beach | VA | 23462 | BGC ID-346341817 | 1973-09-13 | 33-5011356 | 1078-64-867 | 929-235-4055 | ayub244khan@gmail.com |  |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/28-Application Submitted to Lisa |  | RECEIVED | 2025-06-02 | 1286 | 164427 | OK | Y2K ENTERPRISE, INC | MR.JOON YOUNG KIM | 451 E Belt Blvd | Richmond | VA | 23224 |  |  | 37-2148662 | 592-02-2038 | 703-750-0137 | totalbyy2k@gmail.com | 2025-05-28 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/28-Application Submitted to Lisa |  | RECEIVED | 2025-06-02 | 1365 | 164681 | OK | ADAM WIRELESS | MR.SADEK ABDEL AZIZ | 1301 Ward Blvd | Wilson | NC | 27893 |  | 1986-08-03 | 99-4999830 | 085-76-6706 | 252-674-7004 | alex@adamwirelessinc.com | 2025-05-28 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-06 11:00
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  | 5/28-Application Submitted to Lisa |  | RECEIVED | 2025-06-02 | 1093 | 166256 | OK | AZ WIRELESS INC | MR.AYUB KHAN | 4006 Victory Blvd | Portsmouth | VA | 23701 | BGC ID-346341817 | 1973-09-13 | 33-5011356 | 1078-64-867 | 929-235-4055 | ayub244khan@gmail.com |  |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | NEW STORE |  |  |  | RECEIVED | 2025-06-05 | 1874 | 166311 |  | SUCCESS GROUP LLC | MRS.SHALINI KHURANA JAIN | 4900 E Pawnee St | Wichita | KS | 67218 | BGC ID- 347825270 | 1979-08-02 | 93-4520322 | 755-76-8596 | 516-439-1458 | tonib0924@gmail.com | 2025-05-30 |  |  | LEASE | 2025-06-05 | 2025-05-19 | 2025-05-22 | COMPLETED | RECEIVED | 2025-06-05 | YES | PENDING | [23 empty] | gary@pinnaclemobility.com | 2025-06-06 10:26
JUNE-25 | JUNE-25 | NEW STORE |  | 6/4-Floor Plan received, Dealer Approval Pending | [6 empty] | BISMILLAH WIRELESS | MRS.DURRAIN LAKHANI | 8610 Irvington blvd suite A Houston | Houston | TX | 77022 | BGC ID-369485108 | 1982-12-22 | 46-3778254 |  | 281-736-0865 | aly_akb1@hotmail.com | 2025-06-02 |  |  | LEASE | 2025-05-31 | 2025-05-15 | 2025-05-20 | COMPLETED | RECEIVED | 2025-06-04 | YES | APPROVED | 2025-06-04 | [22 empty] | gary@pinnaclemobility.com | 2025-06-04 13:27
JUNE-25 | JUNE-25 | NEW STORE | [8 empty] | DIGITAL UPNY INC | MR. KULWANT SINGH | 800 West Miller St Suit | Newark | NY | 14513 | BGC ID-360428585 | 1990-02-02 | 99-4960986 | 817-75-0758 | 585-500-0002 | digitalupny@gmail.com | 2025-05-29 |  |  |  |  | Not required | Not Required | Not Required | RECEIVED | 2025-06-08 | YES | APPROVED | [23 empty] | gary@pinnaclemobility.com | 2025-06-03 12:45
JUNE-25 | JUNE-25 | NEW STORE |  | 6/4-Application Send to Vanessa | 6/3- Matterport Survey Submitted/Application Send to Dealer for Signature | [5 empty] | DIGITAL UPNY INC | MR. KULWANT SINGH | 1287 E Delavan Ave | Buffalo | NY | 14215 | BGC ID-360428585 | 1990-02-02 | 99-4960986 | 817-75-0758 | 585-500-0002 | digitalupny@gmail.com | 2025-06-04 |  |  | LEASE | 2025-06-03 | 2025-06-03 |  | PENDING | PENDING |  |  | PENDING | [23 empty] | gary@pinnaclemobility.com | 2025-06-05 11:49
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  |  | 6/5- Application Submitted for Ownership change |  |  | 533 |  |  | JNKM SERVICES CORP | MR.ABHIJAT BHASIN | 5238 E TRUMAN RD | KANSAS CITY | MO | 64127 | BGC ID-369371622 | 1975-09-10 | 39-2359362 | 223497071 | 804-385-0452 | bhasinabi@gmail.com | 2025-06-05 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  |  | 6/4- Application Submitted for Ownership change |  |  | 657 |  |  | JNKM SERVICES CORP | MR.ABHIJAT BHASIN | 6823 LONGVIEW RD | KANSAS CITY | MO | 64134 | BGC ID-369371622 | 1975-09-10 | 39-2359362 | 223497071 | 804-385-0452 | bhasinabi@gmail.com | 2025-06-04 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  |  | 6/5- Application Submitted for Ownership change |  |  | 1367 |  |  | JNKM SERVICES CORP | MR.ABHIJAT BHASIN | 12200 15TH ST | GRANDVIEW | MO | 64030 | BGC ID-369371622 | 1975-09-10 | 39-2359362 | 223497071 | 804-385-0452 | bhasinabi@gmail.com | 2025-06-05 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | OWNERSHIP CHANGE |  |  | 6/5- Application Submitted for Ownership change |  |  | 1414 |  |  | JNKM SERVICES CORP | MR.ABHIJAT BHASIN | 11034 E Us Highway 40 | Independence | MO | 64055 | BGC ID-369371622 | 1975-09-10 | 39-2359362 | 223497071 | 804-385-0452 | bhasinabi@gmail.com | 2025-06-05 |  |  | Not Required | Not Required | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | [14 empty] | gary@pinnaclemobility.com | 2025-06-05 09:22
JUNE-25 | JUNE-25 | NEW STORE | [8 empty] | YES WIRELESS LLC | MR.BALWINDER SINGH | 141 N Wellwood Ave | Lindenhurst | NY | 11757 | BGC ID- 350357561 | 1989-12-05 | 99-1359039 |  | 347-776-4444 | YESWIRELESS24@GMAIL.COM | [5 empty] | 2025-05-30 | 2025-06-03 | COMPLETED | PENDING | [26 empty] | gary@pinnaclemobility.com | 2025-06-06 14:05

## Comments
Row 4 | Demo Device Sent on 12/20/24- Fedex Tracking No 770944013812 | Gurwinder Singh | 12/20/24 10:57 AM
Row 8 | TW Application and Agreement Sent to vanessa on 1/7/25 with Matterport Link-https://my.matterport.com/show/?m=jzJphF4ppGm | Gurwinder Singh | 01/07/25 10:39 AM
Row 9 | Pre Install Images | Gurwinder Singh | 01/16/25 7:32 AM
Row 9 | Spectrio Agreement sent to mary on 1/8/25 | Gurwinder Singh | 01/08/25 10:15 AM
Row 9 | Application & Lease sent to Vanessa for 'Floor Plan" 12/20/24 | Gurwinder Singh | 12/20/24 9:10 AM
Row 11 | Matterport Survey Link Sent to Vanessa on 1/7/25 https://my.matterport.com/show/?m=8vBB8f8sUAs | Gurwinder Singh | 01/07/25 2:54 PM
Row 16 | Demo Device Sent on 1/7/25 Tracking ID 771267010535 | Gurwinder Singh | 01/08/25 1:15 PM